## Sheet1
Sprint | View | Sub-View | Est | Assigned | Status | Comment
1 | Header |  | 1
1 | Footer |  | 1
1 | HomePage |  | 2
1 | Additional Info |  | 0
2 | Invite / Email Form |  | 3
2 | Donate |  | 8
2 | Thank You / Receipt |  | 1
1 | Campaign View |  | 8
1 | User Profile Landing Page (new user) |  | 2
1 | User Profile Landing Page (w/campaigns) |  | 4
1 | Edit User Profile |  | 10
1 | User Registration |  | 4
1 | User Registration Additional Info |  | 4
1 | Login |  | 8
2 | Account Recovery |  | 4
1 | Create/Edit Campaign |  | 6
2 | Admin Dashboard |  | 3
3 | Cause Template Management List |  | 0
3 | Create/Edit Cause Template Details |  | 0
2 | Cause Management List |  | 6 |  |  | includes export to Excel
2 | New Cause |  | 2
2 | Edit Cause Details |  | 16
3 | Manage Organization / App Setting |  | 0
3 | User Management List |  | 0
3 | User Info Management |  | 0
3 | Donor Details |  | 0
2 | Campaign List |  | 16
2 | Edit Campaign Details (Admin) |  | 4
| TOTAL |  | 113
| Phase Totals |  |  | Rough Estimation (hours) |  | Est Completion Date
| Total Red Phase (1) | 50 |  | 100 |  | 2011-05-09 12:00 | I need to verify this calculation
| Total Yellow Phase (2) | 63 |  | 126 |  | 2011-08-27 18:00
| Total Blue Phase (3) | 0 |  | 0
| Base Estimation Mutiplier | 2
| StartDate | 2011-02-11
| Week | 7
Formulas:
Comment = C41+([Assigned]/8)*7
Comment = G35+([Assigned]/8)*7
Sub-View = WEEKNUM([Sub-View, row above])

## Sheet2
2011-01-01
15 | 2011-04-09